## Sheet1
SPRINT 1 |  | SPRINT 2 |  | SPRINT 3 |  |  | Sprint 4 |  | Sprint 5
WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 5 | Week 6 |  | WEEK 7 | Week 8 | WEEK 9 | Week 10
Requirement Analysis: Review and understand the new features and user stories. Identify any ambiguities or gaps in the requirements. Test Planning: • Define test objectives and scope • Identify test resources (human, tools, environments) • Develop the test plan document Assumption: Clear and stable requirements for each user story. |  | Test Design & Test-cases: • Review user stories and specifications • Identify test scenarios and test cases for each user story • Create test data and environment requirements. • Create detailed test cases based on user stories and requirements. • Ensure comprehensive coverage of functional and non-functional aspects. Assumption: Detailed user stories available, clear acceptance criteria, test-cases. |  | Test Environment Setup: • Set up test servers, databases, and mobile devices for testing • Install necessary software and configure the test environment • Establish test environments for web and mobile platforms. •Ensure compatibility with different browsers and devices. Assumption: Test environments readily available, minimal configuration required. Test Execution: • Execute test cases, recording results and capturing relevant data. Conduct functional, integration, and system testing. • VerifySearch criteria, user registration, booking, user roles, and mobile application functionalities. Assumption: Adequate time allocated for each testing phase. |  |  | Regression Testing: • Conduct regression testing to ensure existing functionalities are not adversely affected. • Validate that new features integrate seamlessly with the existing system. •Automate regression test suites where applicable to enhance efficiency. Assumption: Efficient automation tools in place, stable codebase. | Performance Testing: • Ensure the system can handle the expected load Assumption: Scalable test environment, cooperation from development for performance tuning. Security Testing: • Validate the security features of the system Assumption: Access to security requirements, collaboration with security experts. | Mobile Application Testing: • Perform testing on the native mobile application. • Ensure compatibility across different devices and operating systems. User Acceptance Testing (UAT): • Collaborate with users to perform UAT on the entire system. • Gather user feedback and address any concerns or issues. • Ensure the system meets user expectations and business requirements. Assumption: Active participation from end-users, quick turnaround for issue resolution. | Test Closure: • Summarize testing activities • Provide test summary report Assumption: Comprehensive test documentation, minimal post-UAT issues.
Assumptions: • Workdays assumed as 5 days per week. • Task dependencies and parallelism are considered in the estimates. • Adequate resources are available throughout the testing process. • The development of new features is completed before the testing phase begins. NOTE:- The provided time estimates are approximations and should be adapted according to the unique project context and the capabilities of the team. It is advised to consistently monitor and adjust the plan as needed during the testing process | [5 empty] | Summing Up the Process:- Planning & Analysis: Understand the requirements and plan the testing approach. Identify potential risks and mitigations. Design & Setup: Create comprehensive test cases, set up the test environment, and prepare necessary test data. Execution & Evaluation: Execute test cases, evaluate results against user stories, and ensure the functionality meets expectations. Mobile & Roles Testing: Specifically address testing for mobile applications and user roles. Integration & Regression: Ensure the seamless integration of new features and perform regression testing to maintain overall system stability. Defect Reporting & Documentation: Report any defects found, collaborate with development for resolution, and document testing activities.